## ProjectSchedule
Data Mining Assignment II - Expedia
Team 77
Winsen Duker, Pepijn Meewis & Tijn Wijdoogen |  | Project Start: | 2018-05-10
|  | Display Week: | 0.05 |  |  | 2018-04-30 08:24 | [6 empty] | 2018-05-07 08:24 | [6 empty] | 2018-05-14 08:24 | [6 empty] | 2018-05-21 08:24 | [6 empty] | 2018-05-28 08:24 | [6 empty] | 2018-06-04 08:24 | [6 empty] | 2018-06-11 08:24 | [6 empty] | 2018-06-18 08:24
 | time axis 2018-04-30 08:24 to 2018-06-24 08:24
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2018-04-30 08:24 to 2018-06-24 08:24
Project duration |  |  | 2018-05-10 | 2018-05-27 | 18
Phase 1: Define and set-up project
Discuss project and main objectives | Team | 100% | 2018-05-10 | 2018-05-10 | 1
Discuss potential steps to be taken | Team | 100% | 2018-05-10 | 2018-05-10 | 1
Create project space: GitHub | Pepijn | 100% | 2018-05-10 | 2018-05-10 | 1 | [56 empty] | Initialise central database and align each computer. Create a well-structured folder structure
Create project planning | Winsen | 100% | 2018-05-10 | 2018-05-10 | 1
Analyse how to handle data | Tijn | 100% | 2018-05-10 | 2018-05-10 | 1 | [56 empty] | Convert to csv to hdf to speed up processing
Phase 2 Data exploration
Research methods of analysing data |  | 100% | 2018-05-10 | 2018-05-13 | 4
Meet to discuss findings |  | 100% | 2018-05-14 | 2018-05-14
Determine how to handle missing data |  | 0% | 2018-05-11 | 2018-05-11 | 1
Task 3 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 4 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 5 |  |  | 2018-05-10 | 2018-05-10 | 1
Phase 3 Data preparation
Task 1 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 2 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 3 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 4 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 5 |  |  | 2018-05-10 | 2018-05-10 | 1
Phase 4 Implementing models
Task 1 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 2 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 3 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 4 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 5 |  |  | 2018-05-10 | 2018-05-10 | 1
Phase 5 Finishing
Task 1 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 2 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 3 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 4 |  |  | 2018-05-10 | 2018-05-10 | 1
Deadline |  | 5% | 2018-05-10 | 2018-05-27 | 18
Insert new rows ABOVE this one
SIMPLE GANTT CHART by Vertex42.com |  |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## Sheet1
Log | Description | Progress | Conclusion
2018-05-10 | Discuss and set-up project | DONE | As the base is set-up, find 2 report each, describing how to handle data and which algos are used
11 May - 13 May | Research methods how to solve
2018-05-14 | Discuss methods how to solve |  | Check distribution of independent variables per book, click & non-clicked and fill data based on these distrbutions
Remove year, min and sec
In paper of Xu, features are removed based on their correlation. However, which one to remove? As this is not named, we could include PCA/CFA
How to convert prices from full stay to daily?