## ProjectSchedule
Data Mining Assignment II - Expedia
Team 77
Winsen Duker, Pepijn Meewis & Tijn Wijdoogen |  | 2018-05-10
|  | 0.05 |  |  | 2018-04-30 08:24 | [6 empty] | 2018-05-07 08:24 | [6 empty] | 2018-05-14 08:24 | [6 empty] | 2018-05-21 08:24 | [6 empty] | 2018-05-28 08:24 | [6 empty] | 2018-06-04 08:24 | [6 empty] | 2018-06-11 08:24 | [6 empty] | 2018-06-18 08:24
 | time axis 2018-04-30 08:24 to 2018-06-24 08:24
TASK | ASSIGNED TO | START | END | DAYS | time axis 2018-04-30 08:24 to 2018-06-24 08:24
Phase I: Define and set-up project
Discuss project and main objectives | Team | 2018-05-07 | 2018-05-07 | 1
Discuss potential steps to be taken | Team | 2018-05-07 | 2018-05-07 | 1
Create project space: GitHub | Pepijn | 2018-05-07 | 2018-05-07 | 1 | [56 empty] | Initialise central database and align each computer. Create a well-structured folder structure
Explore research papers discussing the original case | Tijn | 2018-05-07 | 2018-05-07 | 1
Create project schedule | Winsen | 2018-05-07 | 2018-05-07 | 1 | [56 empty] | Convert to csv to hdf to speed up processing
Analyse research papers found | Team | 2018-05-07 | 2018-05-09
Phase II: Data exploration
Meet to discuss research papers | Team | 2018-05-09 | 2018-05-09 | 1
Determine how to handle the data | Team | 2018-05-09 | 2018-05-09
Analyse dataset statistics and distributions | Winsen | 2018-05-09 | 2018-05-14 | 6
Analyse correlation of features | Tijn & Pepijn | 2018-05-09 | 2018-05-14 | 6
Implement PCA | Tijn & Pepijn | 2018-05-09 | 2018-05-14 | 6
Meet to discuss dataset and correlation results | Team | 2018-05-14 | 2018-05-14
Discuss how to prepare the data | Team | 2018-05-14 | 2018-05-14 | 1
Phase III: Data preparation
Categorise features | Team | 2018-05-14 | 2018-05-14 | 1
Discuss and handle search query-related features | Team | 2018-05-14 | 2018-05-15 | 2
Discuss and handle property-related features | Team | 2018-05-15 | 2018-05-16 | 2
Discuss and handle visitor-related features | Team | 2018-05-15 | 2018-05-16 | 2
Discuss and handle competitor-related features | Team | 2018-05-16 | 2018-05-17 | 2
Phase IV: Implementing models
Discuss models implemented in research papers | Team | 2018-05-09 | 2018-05-09 | 1
Discuss potential models to implement | Team | 2018-05-18 | 2018-05-18 | 1
Implement Linear SVC and XGBoost | Winsen | 2018-05-18 | 2018-05-22 | 5
Implement LightGBM and Random Forest | Pepijn | 2018-05-18 | 2018-05-22 | 5
Implement 7-K Nearest Neighbours and MLP | Tijn | 2018-05-18 | 2018-05-22 | 5
Optimising algorithms | Pepijn | 2018-05-22 | 2018-05-24
Phase V: Finalising documentation
Write data exploration section | Tijn | 2018-05-22 | 2018-05-26 | 5
Write data (pre-)processing section | Winsen | 2018-05-22 | 2018-05-26 | 5
Write model selection section | Pepijn | 2018-05-24 | 2018-05-26 | 3
Write progress report | Team | 2018-05-27 | 2018-05-27 | 1
Hand-in assignment | Winsen | 2018-05-27 | 2018-05-27 | 1
Insert new rows ABOVE this one
SIMPLE GANTT CHART by Vertex42.com |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Note on G6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## Sheet1
Log | Description | Progress | Conclusion
2018-05-10 | Discuss and set-up project | DONE | As the base is set-up, find 2 report each, describing how to handle data and which algos are used
11 May - 13 May | Research methods how to solve
2018-05-14 | Discuss methods how to solve |  | Check distribution of independent variables per book, click & non-clicked and fill data based on these distrbutions
Remove year, min and sec
In paper of Xu, features are removed based on their correlation. However, which one to remove? As this is not named, we could include PCA/CFA
How to convert prices from full stay to daily?

## Sheet2
TASK | ASSIGNED TO | START | END
Phase I: Define and set-up project
Discuss project and main objectives | Team | 2018-05-07 | 2018-05-07
Discuss potential steps to be taken | Team | 2018-05-07 | 2018-05-07
Create project space: GitHub | Pepijn | 2018-05-07 | 2018-05-07
Explore research papers discussing the original case | Tijn | 2018-05-07 | 2018-05-07
Create project schedule | Winsen | 2018-05-07 | 2018-05-07
Analyse research papers found | Team | 2018-05-07 | 2018-05-09
Phase II: Data exploration
Meet to discuss research papers | Team | 2018-05-09 | 2018-05-09
Determine how to handle the data | Team | 2018-05-09 | 2018-05-09
Analyse dataset statistics and distributions | Winsen | 2018-05-09 | 2018-05-14
Analyse correlation of features | Tijn & Pepijn | 2018-05-09 | 2018-05-14
Implement PCA | Tijn & Pepijn | 2018-05-09 | 2018-05-14
Meet to discuss dataset and correlation results | Team | 2018-05-14 | 2018-05-14
Discuss how to prepare the data | Team | 2018-05-14 | 2018-05-14
Phase III: Data preparation
Categorise features | Team | 2018-05-14 | 2018-05-14
Discuss and handle search query-related features | Team | 2018-05-14 | 2018-05-15
Discuss and handle property-related features | Team | 2018-05-15 | 2018-05-16
Discuss and handle visitor-related features | Team | 2018-05-15 | 2018-05-16
Discuss and handle competitor-related features | Team | 2018-05-16 | 2018-05-17
Phase IV: Implementing models
Discuss models implemented in research papers | Team | 2018-05-09 | 2018-05-09
Discuss potential models to implement | Team | 2018-05-18 | 2018-05-18
Implement Linear SVC and XGBoost | Winsen | 2018-05-18 | 2018-05-22
Implement LightGBM and Random Forest | Pepijn | 2018-05-18 | 2018-05-22
Implement 7-K Nearest Neighbours and MLP | Tijn | 2018-05-18 | 2018-05-22
Optimising algorithms | Pepijn | 2018-05-22 | 2018-05-24
Phase V: Finalising documentation
Write data exploration section | Tijn | 2018-05-22 | 2018-05-26
Write data (pre-)processing section | Winsen | 2018-05-22 | 2018-05-26
Write model selection section | Pepijn | 2018-05-24 | 2018-05-26
Write progress report | Team | 2018-05-27 | 2018-05-27