## ProjectSchedule
Data Mining Assignment II - Expedia
Team 77
Winsen Duker, Pepijn Meewis & Tijn Wijdoogen |  | Project Start: | 2018-05-10
|  | Display Week: | 0.05 |  |  | 2018-04-30 08:24 | [6 empty] | 2018-05-07 08:24 | [6 empty] | 2018-05-14 08:24 | [6 empty] | 2018-05-21 08:24 | [6 empty] | 2018-05-28 08:24 | [6 empty] | 2018-06-04 08:24 | [6 empty] | 2018-06-11 08:24 | [6 empty] | 2018-06-18 08:24
 | time axis 2018-04-30 08:24 to 2018-06-24 08:24
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2018-04-30 08:24 to 2018-06-24 08:24
Project duration |  |  | 2018-05-10 | 2018-05-27 | 18
Phase 1: Define and set-up project
Discuss project and main objectives | Team | 100% | 2018-05-10 | 2018-05-10 | 1
Discuss potential steps to be taken | Team | 100% | 2018-05-10 | 2018-05-10 | 1
Create project space: GitHub | Pepijn | 100% | 2018-05-10 | 2018-05-10 | 1 | [56 empty] | Initialise central database and align each computer. Create a well-structured folder structure
Create project planning | Winsen | 100% | 2018-05-10 | 2018-05-10 | 1
Analyse how to handle data | Tijn | 100% | 2018-05-10 | 2018-05-10 | 1 | [56 empty] | Convert to csv to hdf to speed up processing
Phase 2 Data exploration
Research methods of analysing data |  | 0% | 2018-05-10 | 2018-05-11 | 2
Determine how to handle missing data |  | 0% | 2018-05-11 | 2018-05-11 | 1
Task 3 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 4 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 5 |  |  | 2018-05-10 | 2018-05-10 | 1
Phase 3 Data preparation
Task 1 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 2 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 3 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 4 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 5 |  |  | 2018-05-10 | 2018-05-10 | 1
Phase 4 Implementing models
Task 1 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 2 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 3 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 4 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 5 |  |  | 2018-05-10 | 2018-05-10 | 1
Phase 5 Finishing
Task 1 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 2 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 3 |  |  | 2018-05-10 | 2018-05-10 | 1
Task 4 |  |  | 2018-05-10 | 2018-05-10 | 1
Deadline |  | 5% | 2018-05-10 | 2018-05-27 | 18
Insert new rows ABOVE this one
SIMPLE GANTT CHART by Vertex42.com |  |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## Sheet1
Log | Description | Progress | Conclusion
2018-05-10 | Discuss and set-up project | DONE | As the base is set-up, find 2 report each, describing how to handle data and which algos are used